## Project Setup
$200M Data Center Project Controls Portfolio
Project Name | ATL Hyperscale Data Center - Phase 1
Project Type | Mission-Critical Data Center
Location | Atlanta, Georgia (Fictional Portfolio Project)
Baseline Start | 2027-01-01
Baseline Finish | 2028-12-31
Total Project Budget | 200000000
Budget at Completion (BAC) / PMB | 182000000
Management Reserve | 18000000
Currency | USD
Purpose | Portfolio demonstration of project controls, EVM, forecasting, and schedule analytics

## WBS Budget
WBS | Phase | Work Package | Baseline Budget | Planned Start | Planned Finish | Cost Type | Control Account Owner | Weight % | Duration (Days)
1.1 | Preconstruction & General Conditions | Design Management | 2500000 | 2027-01-01 | 2027-06-30 | Indirect | Project Controls | 1.25% | 181
1.2 | Preconstruction & General Conditions | Permits / AHJ / Utility Coordination | 1500000 | 2027-01-01 | 2027-08-31 | Indirect | Project Management | 0.75% | 243
1.3 | Preconstruction & General Conditions | Site Management / Temporary Facilities | 5000000 | 2027-01-01 | 2028-10-31 | Indirect | Field Operations | 2.5% | 670
1.4 | Preconstruction & General Conditions | Project Controls / QA-QC / Safety | 3000000 | 2027-01-01 | 2028-12-31 | Indirect | Project Controls | 1.5% | 731
2.1 | Sitework & Civil | Clearing / Grading / Earthwork | 4000000 | 2027-02-01 | 2027-06-30 | Direct | Civil | 2% | 150
2.2 | Sitework & Civil | Storm / Sanitary / Domestic Water | 4000000 | 2027-03-01 | 2027-09-30 | Direct | Civil | 2% | 214
2.3 | Sitework & Civil | Underground Electrical Ductbank | 5000000 | 2027-04-01 | 2027-10-31 | Direct | Electrical | 2.5% | 214
2.4 | Sitework & Civil | Roads / Paving / Site Concrete | 3000000 | 2027-07-01 | 2028-04-30 | Direct | Civil | 1.5% | 305
3.1 | Foundations & Concrete | Building Foundations | 8000000 | 2027-04-01 | 2027-09-30 | Direct | Structural | 4% | 183
3.2 | Foundations & Concrete | Slabs on Grade | 6000000 | 2027-06-01 | 2027-11-30 | Direct | Structural | 3% | 183
3.3 | Foundations & Concrete | Equipment Pads / Housekeeping Pads | 4000000 | 2027-07-01 | 2028-02-29 | Direct | Structural | 2% | 244
3.4 | Foundations & Concrete | Exterior Concrete / Miscellaneous | 6000000 | 2027-08-01 | 2028-05-31 | Direct | Structural | 3% | 305
4.1 | Structural Steel / Building Envelope | Structural Steel | 12000000 | 2027-07-01 | 2028-01-31 | Direct | Structural | 6% | 215
4.2 | Structural Steel / Building Envelope | Roofing / Waterproofing | 5000000 | 2027-10-01 | 2028-04-30 | Direct | Envelope | 2.5% | 213
4.3 | Structural Steel / Building Envelope | Exterior Wall / Precast / Panels | 7000000 | 2027-09-01 | 2028-05-31 | Direct | Envelope | 3.5% | 274
4.4 | Structural Steel / Building Envelope | Interior Buildout / Architectural | 4000000 | 2028-01-01 | 2028-09-30 | Direct | Architectural | 2% | 274
5.1 | Electrical | Utility Service / MV Equipment | 8000000 | 2027-05-01 | 2028-05-31 | Direct | Electrical | 4% | 397
5.2 | Electrical | Generators | 10000000 | 2027-06-01 | 2028-07-31 | Direct | Electrical | 5% | 427
5.3 | Electrical | Switchgear / UPS / PDU | 11000000 | 2027-07-01 | 2028-08-31 | Direct | Electrical | 5.5% | 428
5.4 | Electrical | Busway / Feeders / Distribution | 9000000 | 2027-11-01 | 2028-10-31 | Direct | Electrical | 4.5% | 366
5.5 | Electrical | Lighting / Branch Power | 5000000 | 2028-01-01 | 2028-10-31 | Direct | Electrical | 2.5% | 305
5.6 | Electrical | Grounding / Lightning Protection | 3000000 | 2027-10-01 | 2028-08-31 | Direct | Electrical | 1.5% | 336
6.1 | Mechanical / HVAC | Chillers / Cooling Plant | 11000000 | 2027-06-01 | 2028-07-31 | Direct | Mechanical | 5.5% | 427
6.2 | Mechanical / HVAC | CRAH / AHU Equipment | 8000000 | 2027-09-01 | 2028-08-31 | Direct | Mechanical | 4% | 366
6.3 | Mechanical / HVAC | Piping / Pumps / Hydronic Distribution | 8000000 | 2027-10-01 | 2028-10-31 | Direct | Mechanical | 4% | 397
6.4 | Mechanical / HVAC | Ductwork / Ventilation | 5000000 | 2028-01-01 | 2028-09-30 | Direct | Mechanical | 2.5% | 274
6.5 | Mechanical / HVAC | Plumbing / Fire Protection | 6000000 | 2027-11-01 | 2028-09-30 | Direct | Mechanical | 3% | 335
7.1 | Controls / Low Voltage / Security | BMS / EPMS Controls | 4000000 | 2028-01-01 | 2028-11-30 | Direct | Controls | 2% | 335
7.2 | Controls / Low Voltage / Security | Telecom / Structured Cabling | 2000000 | 2028-03-01 | 2028-11-30 | Direct | Low Voltage | 1% | 275
7.3 | Controls / Low Voltage / Security | Security / Access Control / CCTV | 2000000 | 2028-04-01 | 2028-11-30 | Direct | Security | 1% | 244
7.4 | Controls / Low Voltage / Security | Fire Alarm / Life Safety Controls | 2000000 | 2028-02-01 | 2028-11-30 | Direct | Low Voltage | 1% | 304
8.1 | Commissioning & Turnover | Level 1-3 Commissioning | 2500000 | 2028-05-01 | 2028-10-31 | Direct | Commissioning | 1.25% | 184
8.2 | Commissioning & Turnover | Level 4-5 Integrated Systems Testing | 3000000 | 2028-08-01 | 2028-12-15 | Direct | Commissioning | 1.5% | 137
8.3 | Commissioning & Turnover | Training / O&M / Closeout | 1500000 | 2028-09-01 | 2028-12-31 | Indirect | Commissioning | 0.75% | 122
8.4 | Commissioning & Turnover | Punchlist / Final Acceptance | 1000000 | 2028-10-01 | 2028-12-31 | Indirect | Project Management | 0.5% | 92
9.1 | Management Reserve | Management Reserve (Outside PMB/BAC) | 18000000 | 2027-01-01 | 2028-12-31 | Reserve | Project Executive | 9% | 731
TOTAL |  |  | 200000000 |  |  |  |  | 100%

## Monthly Baseline
Month | Monthly Planned Value (PV) | Cumulative PV
2027-01-01 | 956439.39 | 956439.39
2027-02-01 | 1756439.39 | 2712878.78
2027-03-01 | 2327867.97 | 5040746.75
2027-04-01 | 4375487.01 | 9416233.76
2027-05-01 | 4990871.63 | 14407105.39
2027-06-01 | 7490871.63 | 21897977.02
2027-07-01 | 9574204.96 | 31472181.98
2027-08-01 | 10174204.96 | 41646386.94
2027-09-01 | 11431149.41 | 53077536.35
2027-10-01 | 11128785.1 | 64206321.45
2027-11-01 | 11709953.93 | 75916275.38
2027-12-01 | 10709953.93 | 86626229.31
2028-01-01 | 12573590.3 | 99199819.61
2028-02-01 | 11059304.58 | 110259124.19
2028-03-01 | 10781526.81 | 121040651
2028-04-01 | 11031526.81 | 132072177.81
2028-05-01 | 10433907.76 | 142506085.57
2028-06-01 | 8440745.37 | 150946830.94
2028-07-01 | 8440745.37 | 159387576.31
2028-08-01 | 7540745.37 | 166928321.68
2028-09-01 | 6190637.14 | 173118958.82
2028-10-01 | 4978515.93 | 178097474.75
2028-11-01 | 2469191.92 | 180566666.67
2028-12-01 | 1433333.33 | 182000000
Baseline KPIs | Value
Total Project Budget | 200000000
BAC / PMB | 182000000
Management Reserve | 18000000

## Data Dictionary
Field / Metric | Definition
BAC | Budget at Completion: total budget in the Performance Measurement Baseline used for EVM; excludes Management Reserve in this portfolio model.
PV | Planned Value: budgeted cost of work scheduled by the status date.
EV | Earned Value: budgeted cost of work actually performed.
AC | Actual Cost: cost incurred for work performed.
CPI | Cost Performance Index = EV / AC.
SPI | Schedule Performance Index = EV / PV.
CV | Cost Variance = EV - AC.
SV | Schedule Variance = EV - PV.
EAC | Estimate at Completion: forecast final project cost.
ETC | Estimate to Complete = EAC - AC.
VAC | Variance at Completion = BAC - EAC.
TCPI | To-Complete Performance Index: required cost efficiency to hit a target.
PMB | Performance Measurement Baseline: time-phased budget used for performance measurement.
Management Reserve | Budget held outside the Performance Measurement Baseline for unknown-unknowns/management control; not earned as EV until formally transferred into scope/budget.