## Executive Summary
$200M Data Center Project Controls — Monthly Status
Status Date: Month 10 of 24 ¦ Fictional portfolio project for project-controls training
Metric | Value | Forecast Metric | Value | Management View | Status
Total Project Authorization | 200000000 | Cost Variance (CV) | 102160000 | Cost | Watch
Performance Measurement Baseline (BAC) | 182000000 | Schedule Variance (SV) | 5260000 | Schedule | Behind
Management Reserve | 18000000 | Estimate at Completion (EAC) | -9879463.3643 | Forecast | Over BAC
Planned Value (PV) | 91640000 | Estimate to Complete (ETC) | -4619463.3643 | Primary Drivers | Switchgear delay; electrical cost pressure; mechanical productivity
Earned Value (EV) | 96900000 | Variance at Completion (VAC) | 191879463.3643 | Overall | Needs corrective action
Actual Cost (AC) | -5260000 | TCPI (to BAC) | 0.45445
Cost Performance Index (CPI) | -18.4221
Schedule Performance Index (SPI) | 1.0574
Analyst Interpretation
At Month 10, the project is earning less value than planned and is spending more than the value earned. CPI below 1.00 indicates cost inefficiency; SPI below 1.00 indicates schedule slippage. The current CPI-based forecast projects a finish above the $182M performance baseline, with the largest pressure coming from electrical procurement/cost growth and mechanical productivity.

## WBS Status
WBS | Control Account | BAC | Planned % | Actual % Complete | Actual Cost | PV | EV | AC | CV | SV | CPI | SPI | EAC | ETC | VAC | Status | Variance Driver
1.0 | Preconstruction & General Conditions | 12000000 | 100% | 100% | 12400000 | 12000000 | 12000000 | 12400000 | -400000 | 0 | 0.96774 | 1 | 12400000 | 0 | -400000 | Complete | Closed slightly over plan due to preconstruction support extension
2.0 | Sitework & Civil | 16000000 | 100% | 100% | 15300000 | 16000000 | 16000000 | 15300000 | 700000 | 0 | 1.0458 | 1 | 15300000 | 0 | 700000 | Complete | Favorable vendor closeout and earthwork efficiency
3.0 | Foundations & Concrete | 24000000 | 90% | 88% | 21800000 | 21600000 | 21120000 | 21800000 | -680000 | -480000 | 0.96881 | 0.97778 | 24772727.2727 | 2972727.2727 | -772727.2727 | Watch | Minor concrete rework and sequence slippage
4.0 | Structural Steel / Envelope | 28000000 | 70% | 63% | 18900000 | 19600000 | 17640000 | 18900000 | -1260000 | -1960000 | 0.93333 | 0.9 | 30000000 | 11100000 | -2000000 | Behind | Steel erection / envelope handoff later than baseline
5.0 | Electrical | 46000000 | 38% | 30% | 15800000 | 17480000 | 13800000 | 15800000 | -2000000 | -3680000 | 0.87342 | 0.78947 | 52666666.6667 | 36866666.6667 | -6666666.6667 | Critical | Switchgear and generator procurement delay; material escalation
6.0 | Mechanical / HVAC | 38000000 | 32% | 26% | 11200000 | 12160000 | 9880000 | 11200000 | -1320000 | -2280000 | 0.88214 | 0.8125 | 43076923.0769 | 31876923.0769 | -5076923.0769 | Watch | Field productivity below plan; rework / overtime pressure
7.0 | Controls / Low Voltage / Security | 10000000 | 15% | 12% | 1500000 | 1500000 | 1200000 | 1500000 | -300000 | -300000 | 0.8 | 0.8 | 12500000 | 11000000 | -2500000 | Watch | Dependent on electrical room release and device procurement
8.0 | Commissioning & Turnover | 8000000 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8000000 | 8000000 | 0 | Not Started | Future phase; no earned value yet
PROJECT TOTALS
TOTAL |  | 182000000 |  |  | 96900000 | 100340000 | 91640000 | 96900000 | -5260000 | -8700000 | 0.94572 | 0.91329 | 198716317.0163 | 101816317.0163 | -16716317.0163 | Needs corrective action | Cost and schedule pressure concentrated in Electrical and Mechanical

## Monthly Trend
Month | Cumulative Planned % | Cumulative Earned % | Cumulative Actual Cost % | PV | EV | AC
1 | 3% | 3% | 2.9% | 5460000 | 5460000 | 5278000
2 | 7% | 6.8% | 6.7% | 12740000 | 12376000 | 12194000
3 | 12% | 11.5% | 11.6% | 21840000 | 20930000 | 21112000
4 | 18% | 17.2% | 17.5% | 32760000 | 31304000 | 31850000
5 | 25% | 23.8% | 24.4% | 45500000 | 43316000 | 44408000
6 | 33% | 30.5% | 31.6% | 60060000 | 55510000 | 57512000
7 | 41% | 36.5% | 38.1% | 74620000 | 66430000 | 69342000
8 | 48% | 41.5% | 43.5% | 87360000 | 75530000 | 79170000
9 | 52% | 46.5% | 48.5% | 94640000 | 84630000 | 88270000
10 | 55.13% | 50.35% | 53.24% | 100340000 | 91640000 | 96900000

## Assumptions
Project Scenario & EVM Data Dictionary
Item | Assumption / Definition | Forecast Formula | Definition
Project | Fictional $200M hyperscale data center | CV = EV - AC | Negative = over cost
Project Authorization | $200M total authorized funding | SV = EV - PV | Negative = behind schedule
BAC / PMB | $182M; management reserve excluded from EVM baseline | EAC = BAC / CPI | Assumes current cost efficiency continues
Management Reserve | $18M; held outside the performance measurement baseline | ETC = EAC - AC | Forecast remaining spend
Status Date | End of Month 10 of a 24-month baseline | VAC = BAC - EAC | Negative = projected overrun
PV | Budgeted cost of work scheduled | TCPI = (BAC-EV)/(BAC-AC) | Efficiency needed on remaining work to still hit BAC
EV | Budgeted cost of work performed
AC | Actual cost of work performed
CPI | EV / AC; below 1.00 indicates cost inefficiency
SPI | EV / PV; below 1.00 indicates schedule slippage